## Sheet1
Team | Constituency | Scheme Name | Duration (Days) | Start Date | End Date | Status | NORMAL STAY | FLYING STAY | UNDER WP HT NORMAL STAY | UNDER CP HT NORMAL STAY | UNDER WP HT FLYING STAY | UNDER CP HT FLYING STAY | MV NORMAL STAY | MV FLYING STAY | TOTAL STAYS
Team -1 | NDARAGWA | CHEPALUNGU | 2 | 2025-07-28 | 2025-07-29 | In Progress | 46 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 49
Team -1 | NDARAGWA | KANGUI MWANGAZA | 2 | 2025-07-30 | 2025-07-31 | In Progress | 51 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 56
Team -1 | NDARAGWA | MUKIRI PESI | 2 | 2025-08-01 | 2025-08-02 | In Progress | 39 | 0 | 1 | 6 | 0 | 0 | 1 | 0 | 47
Team -1 | NDARAGWA | WARUKIRA | 7 | 2025-08-04 | 2025-08-11 | Not Done | 48 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 58
Team -1 | OLJOROROK | CHAKA RELI | 2 | 2025-08-12 | 2025-08-13 | In Progress | 22 | 0 | 0 | 3 | 0 | 0 | 10 | 0 | 35
Team -1 | OLJOROROK | JAMHURI | 7 | 2025-08-14 | 2025-08-21 | Not Done | 7 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 12
Team -1 | OLJOROROK | NYAIROKO PASSENGA | 7 | 2025-08-22 | 2025-08-29 | Not Done | 53 | 0 | 1 | 11 | 0 | 0 | 3 | 0 | 68
Team -1 | OLJOROROK | GWA KARUMBI BAHATI | 1 | 2025-08-30 | 2025-08-30 | Pending | 39 | 0 | 3 | 2 | 0 | 0 | 1 | 0 | 45
Team -1 | OLJOROROK | KWA CHUI | 1 | 2025-09-01 | 2025-09-01 | Pending | 19 | 0 | 4 | 4 | 0 | 0 | 0 | 2 | 29
Team -1 | KINANGOP | IGANJO VILLAGE | 7 | 2025-09-02 | 2025-09-09 | Not Done | 61 | 0 | 0 | 3 | 0 | 0 | 5 | 2 | 71
Team -1 | KINANGOP | MAHI MAHORO | 7 | 2025-09-10 | 2025-09-17 | Not Done | 70 | 0 | 0 | 5 | 0 | 0 | 8 | 4 | 87
Team -1 | KINANGOP | CHURIRI | 1 | 2025-09-18 | 2025-09-18 | Pending | 34 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 38
Team -1 | KINANGOP | LOWER GITHIMA | 1 | 2025-09-19 | 2025-09-19 | Pending | 57 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 61
Team -1 | KINANGOP | MBIRITI | 1 | 2025-09-20 | 2025-09-20 | Pending | 64 | 0 | 1 | 2 | 0 | 0 | 7 | 4 | 78
Team -1 | KINANGOP | KARIAHU | 2 | 2025-09-22 | 2025-09-23 | Complete | 53 | 0 | 0 | 9 | 0 | 0 | 6 | 2 | 70
Team -2 | NDARAGWA | KIHARA VILLAGE | 2 | 2025-07-28 | 2025-07-29 | In Progress | 44 | 0 | 4 | 1 | 0 | 0 | 1 | 0 | 50
Team -2 | NDARAGWA | MURICHU | 2 | 2025-07-30 | 2025-07-31 | In Progress | 32 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 35
Team -2 | NDARAGWA | KIHINGO | 7 | 2025-08-01 | 2025-08-08 | Not Done | 24 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 27
Team -2 | OLJOROROK | AHITI | 7 | 2025-08-09 | 2025-08-16 | Not Done | 43 | 0 | 0 | 3 | 0 | 0 | 7 | 0 | 53
Team -2 | OLJOROROK | BOIMAN KAMBAA | 7 | 2025-08-18 | 2025-08-25 | Not Done | 35 | 0 | 0 | 6 | 0 | 0 | 5 | 3 | 49
Team -2 | OLJOROROK | GATAGATI | 1 | 2025-08-26 | 2025-08-26 | Pending | 31 | 0 | 4 | 1 | 0 | 1 | 2 | 0 | 39
Team -2 | OLJOROROK | GICHAKA VILLAGE | 1 | 2025-08-27 | 2025-08-27 | Pending | 28 | 0 | 4 | 5 | 0 | 0 | 1 | 0 | 38
Team -2 | OLJOROROK | MUTARO KANGUO | 1 | 2025-08-28 | 2025-08-28 | Pending | 61 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 66
Team -2 | OLJOROROK | NEW CELEBRATION | 2 | 2025-08-29 | 2025-08-30 | Complete | 20 | 0 | 1 | 2 | 0 | 0 | 5 | 0 | 28
Team -2 | KINANGOP | KANYAWA VILLAGE | 7 | 2025-09-01 | 2025-09-08 | Not Done | 50 | 0 | 0 | 3 | 0 | 0 | 5 | 2 | 60
Team -2 | KINANGOP | KITIRI VILLAGE | 7 | 2025-09-09 | 2025-09-16 | Not Done | 43 | 0 | 0 | 8 | 0 | 0 | 12 | 4 | 67
Team -2 | KINANGOP | MWEDANDU | 1 | 2025-09-17 | 2025-09-17 | Pending | 31 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 33
Team -2 | KINANGOP | NAIVASHA SUBSTATION | 1 | 2025-09-18 | 2025-09-18 | Pending | 37 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 42
Team -2 | KINANGOP | UPPER MBARUK | 2 | 2025-09-19 | 2025-09-20 | Complete | 91 | 0 | 0 | 7 | 0 | 0 | 13 | 1 | 112
Team -3 | KIPIPIRI | KAMIRANGI VILLAGE | 7 | 2025-07-28 | 2025-08-04 | Not Done | 77 | 0 | 0 | 1 | 0 | 0 | 5 | 1 | 84
Team -3 | KIPIPIRI | LOISE WAITI | 7 | 2025-08-05 | 2025-08-12 | Not Done | 40 | 0 | 0 | 2 | 0 | 0 | 8 | 1 | 51
Team -3 | KIPIPIRI | MANUNGA | 1 | 2025-08-13 | 2025-08-13 | Pending | 30 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 31
Team -3 | KIPIPIRI | TABITHA WANGUI & OTHERS | 1 | 2025-08-14 | 2025-08-14 | Pending | 47 | 0 | 0 | 3 | 0 | 0 | 7 | 3 | 60
Team -3 | KIPIPIRI | FOREST II | 2 | 2025-08-15 | 2025-08-16 | Complete | 61 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 62
Team -3 | OLKALOU | THABA B | 7 | 2025-08-18 | 2025-08-25 | Not Done | 32 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 35
Team -3 | OLKALOU | MUGUMO SELF HELP | 1 | 2025-08-26 | 2025-08-26 | Pending | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33
Team -3 | OLKALOU | RURII | 1 | 2025-08-27 | 2025-08-27 | Pending | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
Team -4 | KIPIPIRI | RIRONI VILLAGE | 7 | 2025-07-28 | 2025-08-04 | Not Done | 33 | 0 | 0 | 7 | 0 | 0 | 6 | 1 | 47
Team -4 | KIPIPIRI | KARIANI | 1 | 2025-08-05 | 2025-08-05 | Pending | 74 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 77
Team -4 | KIPIPIRI | SATIMA WANJOHI VILLAGE | 1 | 2025-08-06 | 2025-08-06 | Pending | 73 | 0 | 1 | 3 | 0 | 0 | 3 | 1 | 81
Team -4 | KIPIPIRI | UPPER NDIARA | 2 | 2025-08-07 | 2025-08-08 | Complete | 73 | 0 | 0 | 1 | 0 | 0 | 11 | 2 | 87
Team -4 | OLKALOU | GITHUNGURI VILLAGE | 7 | 2025-08-09 | 2025-08-16 | Not Done | 37 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 45
Team -4 | OLKALOU | KIRATHIMO | 7 | 2025-08-18 | 2025-08-25 | Not Done | 40 | 0 | 0 | 6 | 0 | 0 | 6 | 5 | 57
Team -4 | OLKALOU | THITAI VILLAGE | 1 | 2025-08-26 | 2025-08-26 | Pending | 52 | 0 | 1 | 6 | 0 | 0 | 2 | 2 | 63