## Sheet1
Team | Constituency | Scheme Name | Duration (Days) | Start Date | End Date | Status | NORMAL STAY | FLYING STAY | UNDER WP HT NORMAL STAY | UNDER CP HT NORMAL STAY | UNDER WP HT FLYING STAY | UNDER CP HT FLYING STAY | MV NORMAL STAY | MV FLYING STAY | TOTAL STAYS
Team -1 | GILGIL | 17013 - K.P.C EBURU CAMP | 7 | 2025-07-28 | 2025-08-04 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -1 | GILGIL | KIAMBOGO 2 | 7 | 2025-08-05 | 2025-08-12 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -1 | KURESOI NORTH | CALF RUBIS IN TOTAL KAMARA WARD | 7 | 2025-08-13 | 2025-08-20 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -1 | KURESOI SOUTH | CHESIRIKWA | 7 | 2025-08-21 | 2025-08-28 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -1 | NAIVASHA | MUNYU, KINUNGI VILLAGE | 7 | 2025-08-29 | 2025-09-05 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -1 | NAIVASHA | NEW KARATI | 7 | 2025-09-06 | 2025-09-13 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -1 | NJORO | KANYANYAINI | 10 | 2025-09-15 | 2025-09-25 | In progress | 76 | 1 | 0 | 4 | 0 | 1 | 4 | 1 | 87
Team -1 | NJORO | MOSOP | 10 | 2025-09-26 | 2025-10-07 | In progress | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87
Team -1 | NJORO | EMAIT/MAUCHE | 7 | 2025-10-08 | 2025-10-15 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -1 | RONGAI | GICHEHA FARM | 7 | 2025-10-16 | 2025-10-23 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -1 | RONGAI | KERMA 2 | 7 | 2025-10-24 | 2025-10-31 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -1 | RONGAI | KINOYO MOGOTIO | 7 | 2025-11-01 | 2025-11-08 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -1 | RONGAI | MATHANGAUTA KIARAGANA | 7 | 2025-11-10 | 2025-11-17 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -1 | SUBUKIA | Edgewood police post | 7 | 2025-11-18 | 2025-11-25 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -1 | SUBUKIA | MIHANGO | 7 | 2025-11-26 | 2025-12-03 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | BAHATI | ARAHUKA SOLAI | 7 | 2025-07-28 | 2025-08-04 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | GILGIL | Konoine | 7 | 2025-08-05 | 2025-08-12 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | KURESOI NORTH | KANGUMU VILLAGE, KERINGET WARD | 7 | 2025-08-13 | 2025-08-20 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | KURESOI NORTH | KARIRIKANIA | 7 | 2025-08-21 | 2025-08-28 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | KURESOI SOUTH | KAMUGORA | 7 | 2025-08-29 | 2025-09-05 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | NAIVASHA | BORESHA VILLAGE | 7 | 2025-09-06 | 2025-09-13 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | NAIVASHA | GITUAMBA | 7 | 2025-09-15 | 2025-09-22 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | NJORO | KIKAPU | 7 | 2025-09-23 | 2025-09-30 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | NJORO | NDEFO LUSERU | 5 | 2025-10-01 | 2025-10-06 | Pending | 69 | 1 | 6 | 1 | 0 | 1 | 0 | 0 | 78
Team -2 | RONGAI | E/RAVINE JUNCTION | 7 | 2025-10-07 | 2025-10-14 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | RONGAI | KANDUTURA | 7 | 2025-10-15 | 2025-10-22 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | RONGAI | KOYOMTICH | 7 | 2025-10-23 | 2025-10-30 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | RONGAI | MATHANGAUTA BAHATI | 7 | 2025-10-31 | 2025-11-07 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -2 | SUBUKIA | KAPTARAKWA | 7 | 2025-11-08 | 2025-11-15 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | GILGIL | 34788 - K.P.C EBURU CAMP | 7 | 2025-07-28 | 2025-08-04 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | GILGIL | KAMBI SWARA KAPKURES | 7 | 2025-08-05 | 2025-08-12 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | KURESOI NORTH | KENJOKETTY PRY | 7 | 2025-08-13 | 2025-08-20 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | KURESOI SOUTH | KAMWAURA | 7 | 2025-08-21 | 2025-08-28 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | KURESOI SOUTH | LAKWENDA | 7 | 2025-08-29 | 2025-09-05 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | NAIVASHA | NGONDI | 7 | 2025-09-06 | 2025-09-13 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | NAIVASHA | RUNDA VILLAGE | 7 | 2025-09-15 | 2025-09-22 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | NJORO | PIAVE 1 | 7 | 2025-09-23 | 2025-09-30 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | NJORO | MWENYERE | 5 | 2025-10-01 | 2025-10-06 | Pending | 39 | 0 | 2 | 1 | 0 | 1 | 1 | 0 | 44
Team -3 | RONGAI | KAPSETEK | 7 | 2025-10-07 | 2025-10-14 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | RONGAI | MATUIKU | 7 | 2025-10-15 | 2025-10-22 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | RONGAI | MOROP | 7 | 2025-10-23 | 2025-10-30 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | RONGAI | NGINYIRIA | 7 | 2025-10-31 | 2025-11-07 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -3 | SUBUKIA | SIMBOYON | 7 | 2025-11-08 | 2025-11-15 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -4 | GILGIL | 51609 - GILGIL | 7 | 2025-07-28 | 2025-08-04 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -4 | GILGIL | KIAMBOGO 1 | 7 | 2025-08-05 | 2025-08-12 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -4 | KURESOI NORTH | MATUMBURU | 5 | 2025-08-13 | 2025-08-18 | Pending | 78 | 1 | 2 | 0 | 0 | 1 | 0 | 0 | 82
Team -4 | KURESOI SOUTH | CHEMANER | 7 | 2025-08-19 | 2025-08-26 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -4 | NAIVASHA | 34242 - MWICIRIGI MARKET KINUNGUI | 7 | 2025-08-27 | 2025-09-03 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -4 | NAIVASHA | MAELA | 7 | 2025-09-04 | 2025-09-11 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -4 | NAIVASHA | MWICHINGIRI | 7 | 2025-09-12 | 2025-09-19 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -4 | NJORO | SUNRISE | 7 | 2025-09-20 | 2025-09-27 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -4 | NJORO | CHEMELUK | 5 | 2025-09-29 | 2025-10-03 | Pending | 52 | 0 | 5 | 2 | 0 | 1 | 0 | 0 | 60
Team -4 | RONGAI | KERMA 1 | 7 | 2025-10-04 | 2025-10-11 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -4 | RONGAI | LELECHWET | 7 | 2025-10-13 | 2025-10-20 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -4 | RONGAI | NGONDU B VILLAGE | 7 | 2025-10-21 | 2025-10-28 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -4 | SUBUKIA | MIHANGO, MAWE MBILI | 7 | 2025-10-29 | 2025-11-05 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team -4 | SUBUKIA | SIMBOYON, KERICHO VILLAGE | 7 | 2025-11-06 | 2025-11-13 | Not Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0